Financial Report

Asiatopia 6/2547

(Period ending December 2004)
___________________________________________________________________________
Balance Sheet
Proposed Budget:   2,000,000 Baht
Budget Plan Details
     1. Asiatopia Festival, 6/Nov 2004
 



553,000 
Baht

1.1 Artist




186,000

1.2 Transportation & Accom.


  84,000

1.3 Documentation



115,000

1.4 Co-ordination



168,000
     2. Post festival program: Nov 2004-Apr 2005

         1,447,000
Baht

2.1 Critical research : 



140,000

      (Looking Back to Asiatopia1998-2003)



2.2 Regional Seminar : 

         1,307,000

      (Performance Art in S.E Asia / 



 
      The Movement & Future)
Actual Receive








20-12-2004 Transfered to the bank
                             1,952,413.95 
Baht

Actual Expenditure Details
   1. Asiatopia Festival,6/Nov 2004



         553,600.30
Baht

    
1.1  Artist: 



      101,884.25

1.2 Transportation & Accom. 

        36,264. -

1.3  Documentation


      166,955.50

1.4  Co-ordination


      248,496.55
     2. Post festival program: Nov 2004-Apr 2005

          141,000. -- 
Baht


2.1  Critical research :

    
       (Looking Back to Asiatopia 1998-2003)





2.2  Regional Seminar : 



         ………. ......
Baht
Total expenses 





          694,600.30
Baht
Balance forward to next period (2.2 Regional Seminar)
       1,257,813.65
Baht
[image: image1.jpg]





Project Co-ordinator
…………………    (Chumpon  Apisuk)





 28 / 04 / 2005

[image: image2.jpg]






Accountant…   (Sunee  Phungphaisarn)



 





    28/04/2005
