Book and DVD Documentary Proposal

ASIATOPIA and Contemporary Performance Art in Southeast Asia

Concept

ASIATOPIA, an international contemporary performance art festival in Thailand, has been held every year since 1998. To mark the fifth anniversary, it is proposed to produce a publication which discusses this event within the context of contemporary performance art in Southeast Asia.

 Each year approximately thirty international artists are invited to participate in ASIATOPIA and the event is becoming known widely as the most successful and interesting performance art gathering.

There is very little documentation of contemporary performance art in Southeast Asia.

This publication will investigate the messages and styles within the art and give background on significant artists. A printed document with text and photos is complemented with a DVD (one hour) with edited highlights of ASIATOPIA performances.

Aim: To document the historical development of Asiatopia (from 1998-2003) within the 

context of the development of contemporary performance art in Southeast Asia.
Creative Team

Team Leader: Chumpon Apisuk

Writers and Editors: Joseph Ng, Thanom Chipakdee, Virginia Henderson

DVD Editor: Morokot (to edit 100 hours into one hour DVD) = 200 hours work

Designers: to be decided

Resources on hand

Approximately 100 hours of video footage of the past five years (20 hours per year)

Documentation of Asiatopia events (1998-2003)

Project Timeframe: October 2003-May 2004
	Period
	Action
	

	October-December 2003


	Research:

Review of literature currently available on contemporary performance art. Background of other international festivals and movements in Asia and the rest of the world (Quebec, Scotland, Brazil, Cologne, etc.) 

Profiles of significant Southeast Asian artists (Tang Da Wu, Arahmayani, Amanda Heng, Heri Dono, etc.)


	Joseph, Thanom, Chumpon, Virginia



	November 2002 –January 2004


	Writing
	Joseph and Thanom, (Apinan Poshyananda)

	February-March 2004 


	Editing
	Virginia and Chumpon

	April 2004 


	Layout and Design
	To be decided

	May 2003 


	Printing 


	To be decided


Proposed Book Format

8 inches by 9 inches (B&W) – one color

Number of pages: 200 

Number of Copies: 1000

Proposed Budget

Research (October –December 2003) 3 months, 4 people 10,000 baht/month

Writing  (November-January 2004) 2 months, 2 people  20,000 baht/month
Editing (February-March 2003) 2 months, 2 people, 20,000 baht/month 

Layout and Design  40,000 baht

DVD Editing 200 hours @ 8 hours per day @10,000 baht/day = 250,000 baht
Total Budget                   ???
